## Basic Template
|  |  |  | Project Leader: |  |  | Project: Checkers | [14 empty] | Date: 11/07/2013
Project Objective: Create a Checkers game for 1 (vs AI) or 2 players (Player vs Player).
Objectives |  |  |  |  | Major Tasks |  | Project Completed By: 12/2/2013 | [11 empty] | Owner
|  |  |  | 1 | Map out how the game will function |  | O | [11 empty] | A | A | A
|  |  |  | 2 | Phase 1 Sketch out the UI and game elements |  |  | O | [10 empty] | B | A | B
|  |  |  | 3 | Phase 1 Create UML Diagrams |  |  |  | O | [9 empty] | B | A | B
|  |  |  | 4 | Phase 2 Implement Game Logic | [6 empty] | O | [6 empty] | A | B | B
|  |  |  | 5 | Phase 3 Create UI | [11 empty] | O |  | B | B | A
|  |  |  | 6 | Phase 3 Create AI | [11 empty] | O |  | A | B | B
|  |  |  | 7 | Phase 4 Code Review | [12 empty] | O | A | A | A
|  |  |  | 8 | Phase 5 Finish Documentation | [12 empty] | O | B | A | B
|  |  |  | 9 | Phase 6 Upload Final code | [12 empty] | O | A | A | A
10
11
12
13
14
15
16
17
18
19
20
21
22
23
|  |  |  | A | Initial Design + Framework | [13 empty] | A | A | A | A
|  |  |  | B | Gameboard/Game Rules/Implementation | [13 empty] | A | B | B | B
|  |  |  | C | AI | [13 empty] | B | B | B | A
|  |  |  | D | Graphical User Interface | [13 empty] | B | B | A | B
|  |  |  | E | Documentation/Optimization/Maintenance | [13 empty] | B | A | B | B
# People working on the project: 4
Design & Document | Agile Phase 1 (Board/Game Logic) | Agile Phase2 (GUI, Graphics, Visual Design) | Agile Phase 3 (Documentation, Optimization) |  |  |  | 2013-09-11 | 2013-09-18 | 2013-09-25 | 2013-10-02 | 2013-10-09 | 2013-10-16 | 2013-10-23 | 2013-10-30 | 2013-11-06 | 2013-11-13 | 2013-11-20 | 2013-11-27 | Kendall Zettlmeier | Andrew Guillen | Shane Lopez | Bill Kukowski
[7 empty] | 2013-10-23: O; 2013-10-30: expected task activity here | A = primary owner
[7 empty] | 2013-10-23: O; 2013-10-30: no progress or stuck | B = secondary owner
[13 empty] | O | in progress
[13 empty] | O | completed
Version: 11/07/2013
Version: 11/30/2013
Adapted from OPPM: www.onepageprojectmanager.com